## Week1
Project Title: Milestone 2 Release #: 1.0 Sprint #: 2
| # | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I would like my users to have a landing page that requests they login or register | index page | Tim | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
| 2 | As a dev I need a page that allows users to login to their account | login page | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 3 | As a dev I need a paage that allows users to create an account | register page |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 4 | As a dev I would likt to provide users with the ability to create or edit posts | create new/ edit post page |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 5 | As a dev I need a page that displays all active posts created by users in one area | post feed page |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 6 | As a dev I need a page that allows users to edit their profile details and/ or select if they would like to create or edit posts | my profile page |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 7 | As a dev I would like to provide users with a list of all active posts created by them so they can edit the content | post management page |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 8 | As a dev I would like to have a page that displays one post in a readable manner after a user clicks on a post from the post feed page | view post page |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 9 | As a dev I would like to store all post information as well as user account information in a connected database. These tables should be connected via a foriegn key for ease of connecting users with specific posts. This task will include a DDL script. | MySQL database | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | As a dev I would like an app server to provide an API for interacting with the database and its tables | Build Node.js API Routes and Server Peripherals | Daniel | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0
|  | As a dev I would like general tooling for viewing hot-reloaded changes and testing features locally before bundling and deployment. | Figure out stack tools/structure | Daniel | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
| 10 | As a dev I would like a high level video overview of the code, webdesign, and features for presenting current progress. | Loom Video presentation (8 -10 Minutes) | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 11 | As a group we should know who will do the final submit ahead of time to ensure a timely submission. Submission instructions are in the #resources page on Discord chat room. | Final Submission to Loud Cloud |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 22 | 18.8571 | 15.7143 | 12.5714 | 9.4286 | 6.2857 | 3.1429 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 22 | 22 | 21 | 21 | 21 | 21 | 15 | 7

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0