## Week1
Project Title: Milestone 1 Release #: 1.0 Sprint #: 1
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I would like to have an outline of: the kind of website (blog), functionality of website (Posts managed by users), and products on website (blog posts) | Detailed writeup of website(blog Website) | Daniel/Tim | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 2 | As a dev I would like to have a layout of the websites pages | Sitemap | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 3 | As a dev I would like to have a general mockup of the website design | Wireframe Designs | Tim | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
| 4 | As a dev, I would like to have ER, UML, and site flow diagrams as a basis for project architecture. | Data diagrams, Site link diagrams | Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| 5 | As a dev, I would like to have a write up of all the languages, tools, frameworks, and libraries (and their versions) used in this project. | Write up section in project documentation on tooling | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 6 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 8 | 8 | 8 | 8 | 7 | 5 | 0 | 0

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0